## Communications Plan
EVENT NAME:
Step | Key Message | Audience | Platform / Channel | Assets | Date to Send / Publish | Responsible Person | Status
1
2
3
4
5
6
7

## Completed
EVENT NAME: Alpha Come & See BBQ
Step | Key Message | Audience | Platform / Channel | Assets | Date to Send / Publish | Responsible Person | Status
1 | Save the date – event is coming | Alpha Alumni, mailing list, parish community, friends, family | Email newsletter, social media post - Insta/FB | Newsletter content, social media tile | 6 weeks before event | Comms Officer | Complete
2 | Event details – theme, speakers, program, BBQ menu | Target participants, partners, community groups | Website update, flyer, email blast | Event flyer with photos of last event, QR code for registration | 4 weeks before event | Event Manager | In progress
3 | Registration reminder – secure your place | Those who have not registered | Email reminder, social media boost - Insta/FB | Message content, photos, online registration link | 2 weeks before event | Comms Officer | In progress
4 | Countdown & teaser – highlight key attraction/speaker | All registered attendees + broader audience | Instagram/FB | Key speaker photo, social media tile | 1 week before event | Social Media Lead | Not started
5 | Final information - logistics (time, venue, parking, online link) | Registered attendees | Direct email | Message content | 3 days before event | Event Manager | Not started
6 | Live updates / engagemnts | Attendees & online followers, partners, sponsors | Social media, live tweets | Photos, social media stories | On event day | Social Media Lead | Not started
7 | Thank you + post-event highlights | All participants, partners, sponsors | Email, website news, social media | Message content, photos, social media tile | 2-3 days after event | Comms Officer | Not started